## Action Plan
Technician Commitment Action Plan for the University of Cambridge 2020-23 as at 25-11-20
|  |  | Phase 1 - 2021 |  |  |  | Phase 2 - 2022 |  |  |  | Phase 3 - 2023
Action number | Action | Who | Jan-21 | Apr-21 | Jul-21 | Oct-21 | Jan-22 | Apr-22 | Jul-22 | Oct-22 | Jan-23 | Apr-23 | Jul-23 | Oct-23 | Status (RAG)
no data | Overarching Actions
1 | Maintain regular liaison with Technician Champion | SP/TCC | [12 empty] | Ongoing/in progress
2 | Contribute to the Technician Agenda Steering Group led by Professor David Cardwell | SP/TCC | [12 empty] | Ongoing/in progress
3 | Review and refine governance of the Technician Commitment at Cambridge | SP/DC | [12 empty] | Action needed - 1
4 | Establish TC co-ordinator and administrative support to drive this action plan | SP | [12 empty] | Action needed - 1
5 | Review of line management arrangements for technicians and make recommendations to ensure involvement of technical/professional service managers in addition to academics | tbc | [12 empty] | Action needed - 2
6 | Identify initiatives to increase number of BAME technicians in the University | tbc | [12 empty] | Action needed - 2
no data | Visibility
7 | Communicate the aims of the Technician Commitment widely across the University | TCC | [12 empty] | Action needed - 2
8 | Develop the Technician Commitment website as the 'go to' place for technicians to support their development, career progression, networking and access to resources | TCC | [12 empty] | Action needed - 2
9 | Use Yammer and other forums to communicate with technicians and key stakeholders | TCC | [12 empty] | Ongoing/in progress
10 | Support and promote the work of the Technician Commitment Working Group | SP/TCC | [12 empty] | Ongoing/in progress
no data | Recognition
11 | Run an ongoing poster campaign (including virtual) to recognise and promote the key contribution of technicians | TCC | [12 empty] | Ongoing/in progress
12 | Utilise University wide wesbites and the Technicians Make it Happen website, to promote the work of technicians and opportunities for technicians | TCC | [12 empty] | Action needed - 2
13 | Support technicians with gaining professional registration status | TCC | [12 empty] | Ongoing/in progress
14 | Establish a Technician Recognition Scheme based on the annual Professional Services Recognition Scheme | SP/TCC | [12 empty] | Action needed - 2
15 | Encourage nominations for local and national awards eg Times Higher | TCC | [12 empty] | Ongoing/in progress
no data | Career Development
16 | Deliver Technician Networking events regularly through the year | TCC | [12 empty] | Ongoing/in progress
17 | Deliver a Technician Conference every 2 years (following the inaugural event in 2019) | TCC | [12 empty] | Ongoing/in progress
18 | Maintain links with appropriate national bodies and their resources eg Higher Education and Technicians Education Development (HEaTED), National Technician Development Centre (NTDC) | SP/TCC | [12 empty] | Ongoing/in progress
19 | Identify and share best practice with regard to technician development and progression in departments | TCC | [12 empty] | Action needed - 2
20 | Extend the Online Career Development Tool (based on Lexonis) to include technician skills and attributes, and engage technicians with this | PPD/TCC | [12 empty] | Action needed - 2
21 | Identify gaps in the training available for technicians; introduce new and updated training in response | PPD/TCC | [12 empty] | Action needed - 2
22 | Consider setting up a Mentoring Pilot Scheme for technicians | PPD/TCC | [12 empty] | Action needed - 2
no data | Sustainability
23 | Support the West Cambridge Technician Apprenticeship Project and its roll out to other sites | CL | [12 empty] | Action needed - 2
24 | Collate and publicise technician apprenticeship vacancies to increase visibility of technical roles available | CL | [12 empty] | Action needed - 2
25 | Increase outreach activities with local schools/colleges to promote technician careers and work experience, including Cambridge Academy for Science and Technology | CL | [12 empty] | Action needed - 2
26 | Identify potential technician and skill shortage areas, following review of age, gender, race, grade and role profile data; highlight actions required | TCC/CL | [12 empty] | Action needed - 2
27 | Produce roadmap of key career stages for technicians from apprenticeships upwards | TCC/CL | [12 empty] | Action needed - 2
28 | Promote use of the Workforce Planning guide to support succession planning at departmental level | TCC | [12 empty] | Ongoing/in progress
no data | Evaluating Impact
29 | Establish evaluation criteria to measure success of the Technician Commitment at Cambridge eg turnover, promotions, skills shortages, take up of training and professional registration, success stories, anecdotal evidence. | TCC | [12 empty] | Action needed - 2
30 | Complete annual evaluation report for relevant bodies eg Technician Agenda Steering Group, Personal and Professional Development Committee, include progress against metrics; lessons learnt, targets for future years | SP/TCC | [12 empty] | Action needed - 2
31 | Review and update action plan with input from TC Working Group, Technician Champion and technicians | SP/TCC | [12 empty] | Ongoing/in progress
Who
DC: David Cardwell, Technician Champion and PVC
SP: Sue Pandey, Head of Learning and Development, PPD
TCC: Technician Commitment Co-ordinator
VH: Vickie Hayton, Technician representative
CL: Colin Long, Apprenticeship Manager, PPD
KBP: Katie Bright-Ramon Pelegrin, Online Develoment Manager
WG: Technician Commitment Working Group
PPD:Personal and Professional Development team
RAG
Action needed - priority 1
Action needed - priority 2
Ongoing/in progress
End of worksheet